## Estimation
CLAIMATE PRIME HMO V1 - TIME LINE
Modules | Hours |  |  | This project WAS STOPPED by MANU on 06-Sep-2013 Friday
| DEV | UAT
SUFEEL asked to create a new project
MAIN DASHBOARD | 16 | 12
PMIS ISSUES (21) | 24 | 18
EXCEL REPORTS SEPARATE THREAD | 144 | 108
TOTAL ESTIMATE | 184 | 138
TOTAL USED | 176 | 61
BALANCE | 8 | 77
EXPECTED DATE |  | 2013-09-16 03:02 | *Note:- Based on employees leave and other work allocation, this dead line will be extended.
Update 1:- Developers are new to WPF application and so they are facing many difficulties while devloping Excel Reports Separate Thread
So that, for Bugfixing they are expecting 80 hours more. That hours are added here => 64 + 80 : 144. (23-Aug-2013)

## DEV
*Note:- If the developer did other than these scheduled works, that time would not be reflected here. Those worked times were reflected only in the corresponding day daily status report excel
DATE | HOURS
| SENTHIL S R | SHARON J | SAILEKSHMY N G | RATHEESH R | *Note:- IT Support & DBA worked times would be reflected only at daily status report excel
2013-08-12 | 0 | 0.5 | 0 | 0
2013-08-13 | 0 | 4.5 | 0 | 0
2013-08-14 | 0 | 10 | 0 | 0
2013-08-15 | 0 | 0 | 0 | 0
2013-08-16 | 0 | 0 | 3 | 0
2013-08-17 | 0 | 0 | 0 | 0
2013-08-18 | 0 | 0 | 0 | 0
2013-08-19 | 2 | 8 | 6 | 0
2013-08-20 | 1 | 8 | 4 | 0 | This project WAS STOPPED by MANU on 06-Sep-2013 Friday
2013-08-21 | 4 | 10 | 8 | 0
2013-08-22 | 2 | 8 | 8 | 0 | SUFEEL asked to create a new project
2013-08-23 | 1 | 7 | 7 | 0
2013-08-24 | 0 | 0 | 0 | 0
2013-08-25 | 0 | 0 | 0 | 0
2013-08-26 | 0 | 5 | 7 | 0
2013-08-27 | 0 | 8 | 8 | 0
2013-08-28 | 2 | 8 | 8 | 0
2013-08-29 | 4 | 8 | 8 | 0
2013-08-30 | 0 | 0 | 2 | 0
2013-08-31 | 0 | 0 | 0 | 0
2013-09-01 | 0 | 0 | 0 | 0
2013-09-02 | 0 | 0 | 1 | 0
2013-09-03 | 0 | 0 | 2 | 0
2013-09-04 | 0 | 0 | 3 | 0
2013-09-05 | 0 | 0 | 0 | 0
2013-09-06 | 0 | 0 | 0 | 0
2013-09-07 | 0 | 0 | 0 | 0
2013-09-08 | 0 | 0 | 0 | 0
2013-09-09 | 0 | 0 | 0 | 0
2013-09-10 | 0 | 0 | 0 | 0
2013-09-11 | 0 | 0 | 0 | 0
2013-09-12 | 0 | 0 | 0 | 0
2013-09-13 | 0 | 0 | 0 | 0
2013-09-14 | 0 | 0 | 0 | 0
2013-09-15 | 0 | 0 | 0 | 0
2013-09-16 | 0 | 0 | 0 | 0
2013-09-17 | 0 | 0 | 0 | 0
2013-09-18 | 0 | 0 | 0 | 0
2013-09-19 | 0 | 0 | 0 | 0
2013-09-20 | 0 | 0 | 0 | 0
2013-09-21 | 0 | 0 | 0 | 0
2013-09-22 | 0 | 0 | 0 | 0
2013-09-23 | 0 | 0 | 0 | 0
2013-09-24 | 0 | 0 | 0 | 0
2013-09-25 | 0 | 0 | 0 | 0
2013-09-26 | 0 | 0 | 0 | 0

## UAT
DATE | HOURS |  |  | *Note:- If the tester did other than these scheduled works, that time would not be reflected here. Those worked times were reflected only in the corresponding day daily status report excel
| VARUN V | AMALA T | RITU A
2013-08-28 | 4 | 2 | 2
2013-08-29 | 8 | 8 | 0 | This project WAS STOPPED by MANU on 06-Sep-2013 Friday
2013-08-30 | 0.5 | 1 | 0.5
2013-08-31 | 0 | 0 | 0 | SUFEEL asked to create a new project
2013-09-01 | 0 | 0 | 0
2013-09-02 | 0 | 2 | 1.5
2013-09-03 | 2.5 | 2 | 3
2013-09-04 | 8 | 8 | 8
2013-09-05 | 0 | 0 | 0
2013-09-06 | 0 | 0 | 0
2013-09-07 | 0 | 0 | 0
2013-09-08 | 0 | 0 | 0
2013-09-09 | 0 | 0 | 0
2013-09-10 | 0 | 0 | 0
2013-09-11 | 0 | 0 | 0
2013-09-12 | 0 | 0 | 0
2013-09-13 | 0 | 0 | 0
2013-09-14 | 0 | 0 | 0
2013-09-15 | 0 | 0 | 0
2013-09-16 | 0 | 0 | 0
2013-09-17 | 0 | 0 | 0
2013-09-18 | 0 | 0 | 0
2013-09-19 | 0 | 0 | 0
2013-09-20 | 0 | 0 | 0
2013-09-21 | 0 | 0 | 0
2013-09-22 | 0 | 0 | 0
2013-09-23 | 0 | 0 | 0
2013-09-24 | 0 | 0 | 0
2013-09-25 | 0 | 0 | 0
2013-09-26 | 0 | 0 | 0
2013-09-27 | 0 | 0 | 0
2013-09-28 | 0 | 0 | 0
2013-09-29 | 0 | 0 | 0
2013-09-30 | 0 | 0 | 0
2013-10-01 | 0 | 0 | 0
2013-10-02 | 0 | 0 | 0
2013-10-03 | 0 | 0 | 0
2013-10-04 | 0 | 0 | 0
2013-10-05 | 0 | 0 | 0
2013-10-06 | 0 | 0 | 0
2013-10-07 | 0 | 0 | 0
2013-10-08 | 0 | 0 | 0
2013-10-09 | 0 | 0 | 0
2013-10-10 | 0 | 0 | 0
2013-10-11 | 0 | 0 | 0
2013-10-12 | 0 | 0 | 0